## Sheet1
Tasks | Start Date | Duration | Gantt Chart
Requirement Gathering | 2020-09-15 | 7
Brain Stroming | 2020-09-22 | 10
Scope Identification | 2020-10-02 | 4
Proposal Submission | 2020-10-07 | 3
Requirement Analysis | 2020-10-10 | 5
First Deliverable | 2020-10-15 | 20
Second Deliverable | 2020-11-05 | 27
Third Deliverable | 2020-12-04 | 40
Project Review | 2021-01-14 | 7
Software Design | 2021-01-22 | 10
Development | 2021-02-03 | 20
Testing | 2021-02-24 | 4
Deployment | 2021-03-01 | 2
Maintenance and Supportablility | 2021-03-04 | 7